## UAT Plan
UAT Strategy Overview - Final Testing Cycle
This page outlines the acceptance testing framework for validating key functionalities prior to dashboard release.
Project Name: | Omnichannel Retail Behaviour and Performance Analytics Dashboard
Objective: | To validate that the dashboard meets all functional requirements and business expectations before final deployment or project closure.
Scope of Testing: | UAT covers key functionalities like Summary insights, KPI filtering, campaign and ticket analysis, and rolebased access validations.
Out of Scope: | Backend ETL, external source system validation, and infrastructure performance testing.
Test Environment: | Power BI Service (workspace or shared link)
UAT Team: | 1. Priya Ramanathan (Project Sponsor)
2. Sudhagar (Business Intelligence Engineer/UAT Coordinator)
3. Sales Manager
4. Support Manager
5. Marketing Analyst
Test Schedule: | Start Date: 26-Jul-2025
End Date: 29-Jul-2025
Entry Criteria: | 1. Final Power BI report is published
2. Test data loaded and validated
3. Test cases are documented and reviewed
Exit Criteria: | 1. All test cases executed
2. All high/medium severity defects resolved
3. Signoff received from stakeholders
Test Deliverables: | 1. Test Cases matrix
2. Defect Tracker
3. Traceability matrix
4. Summary report
5. Sign-off
Risk/Assumptions: | 1. Stakeholders are available for timely feedback
2. Test data is representative of real scenarios
3. No change in requirements during UAT
Approvers: | 1. Deepa Menon (Strategic Approver - Sales Governance)
2. Priya Ramanathan (Project Sponsor)
3. Sudhagar (Business Intelligence Engineer/UAT Coordinator)

## UAT Test Cases
UAT Test Case Matrix - Dashboard Validation | [6 empty] | Status: |  | Tester:
1. This section documents the user acceptance testing scenarios mapped to user stories. | [6 empty] | Passed |  | Sudhagar
2. It ensures coverage across roles, report pages and functionality defined in the BRD. | [6 empty] | Failed |  | Name
Pending
Test Case ID | User Story ID | Test Scenario | Test Steps | Expected Result | Role | Report Page | Status | Defect ID | Comments | Tested By | Date Executed
TC-01 | US-01 | Validate Summary page insights load correctly | 1. Login as Project Sponsor; 2. Navigate to Summary page | Summary cards display narrative on Revenue, Customers, Campaigns, and Support | Project Sponsor | Summary | Passed | N/A | N/A | Sudhagar | 2025-07-29
TC-02 | US-02 | Verify Overview KPIs filter by Year/Quarter/Month | 1. Login as Project Sponsor; 2. Navigate to Overview; 3. Change date slicer values | KPI visuals update based on selected time period | Project Sponsor | Overview | Passed | N/A | N/A | Sudhagar | 2025-07-29
TC-03 | US-03 | Monitor churn by age group | 1. Login as Project Sponsor; 2. Go to Overview; 3. Apply churn period slicer; 4. View churn by age | Churn visuals show breakdown by age group and slicer works | Project Sponsor | Overview | Passed | N/A | N/A | Sudhagar | 2025-07-29
TC-04 | US-04 | Validate Deepa’s strategic view | 1. Login as Deepa Menon; 2. Open Summary & Overview; 3. Review revenue, campaign and churn visuals | Visuals align with strategic goals and support final approval | Strategic Reviewer | Summary, Overview | Passed | N/A | N/A | Sudhagar | 2025-07-29
TC-05 | US-05, US-06 | Verify revenue split by region and product category | 1. Login as Sales Manager; 2. Go to Revenue page; 3. Filter by region or product | Revenue visuals show correct breakdown by region and category | Sales Manger | Revenue | Passed | N/A | N/A | Sudhagar | 2025-07-29
TC-06 | US-08, US-09 | View top products and product ratings | 1. Login as Sales Manager; 2. Navigate to Products; 3. View top products and rating visuals | Visuals show top 10 products by revenue and correct average ratings | Sales Manger | Products | Passed | N/A | N/A | Sudhagar | 2025-07-29
TC-07 | US-10, US-11, US-12 | Validate Campaign ROI and channel performance | 1. Login as Marketing Analyst; 2. Go to Campaigns page; 3. Review ROI, conversions, and channel performance | Charts show ROI, conversion %, and channel-level metrics as per filters | Marketing Manager | Campaigns | Passed | N/A | N/A | Sudhagar | 2025-07-29
TC-08 | US-15, US-16, US-17 | Track ticket volume and SLA resolution | 1. Login as Support Manager; 2. Go to Support Tickets page; 3. Validate volume and SLA visuals | Ticket and SLA visuals reflect accurate resolution metrics | Support Manager | Support Tickets | Passed | N/A | N/A | Sudhagar | 2025-07-29
TC-09 | US-19, US-20, US-21 | Analyze retention, churn by age/channel | 1. Login as Support Manager; 2. Go to Customers page; 3. Check retention, churn by age group and preferred channel | Visuals show repeat customers, churn segments and top customers | Support Manager | Customers | Passed | N/A | N/A | Sudhagar | 2025-07-29
TC-10 | US-22, US-23 | QA of filters and narrative definitions | 1. Login as Business Intelligence Engineer; 2. Review Summary and all pages; 3. Match metrics to documentation | KPI logic, filters and definitions match the documentation | Business Intelligence Engineer | Summary, All Pages | Passed | N/A | N/A | Sudhagar | 2025-07-29
TC-11 | US-25 | Test scheduled data refresh | 1. Login as Data Engineer; 2. Check refresh schedule in Power BI Service; 3. Confirm successful refresh and log entries | Data updates correctly based on scheduled time | Data Engineer | Back-end | Passed | N/A | N/A | Sudhagar | 2025-07-29
TC-12 | US-27 | Validate role-based access (RLS) | 1. Login with each stakeholder role; 2. Confirm data visibility is restricted as per role definition | Each role sees only the pages and data relevant to them | Data Engineer | All Pages | Passed | N/A | N/A | Sudhagar | 2025-07-29

## UAT Test Cases Summary
UAT Execution Summary - Test Case Completion by Role & Status
1. This sheet consolidates test case counts across user roles and current execution status.
2. It supports traceability to BRD coverage and defect logging.
Note: To view the latest results, please click ‘Refresh’ on the pivot tables
| Role | Number of Test Cases |  | Status | Number of Test Cases
| Project Sponsor | 3 |  | Passed | 12
| Support Manager | 2 |  | Grand Total | 12
| Sales Manger | 2
| Data Engineer | 2
| Strategic Reviewer | 1
| Marketing Manager | 1
| Business Intelligence Engineer | 1
| Grand Total | 12

## UAT Defect Tracker
UAT Execution - Defect Tracker |  |  | Severity: |  | Status: |  | Resolution:
1. This sheet outlines the defect management structure used during UAT. |  |  | Critical |  | New |  | Fixed
2. No defects were encountered, and all scenarios executed successfully. |  |  | High |  | In Progress |  | Won't Fix
|  |  | Medium |  | Resolved |  | Workaround Provided
|  |  | Low |  | Closed |  | Duplicate Merged
|  |  | Not Applicable |  | Not Applicable |  | Not a Defect
Not Applicable
Defect ID | Description | Linked Test Case | Severity | Status | Resolution | Logged By | Date Logged | Comments
DEF-00 | No defects were found during testing. | All | Not Applicable | Not Applicable | Not Applicable | Sudhagar | 2025-07-29 | All test scenarios passed.

## UAT Traceability
UAT Traceability Matrix - User Stories to Test Case Coverage | [6 empty] | Status:
1. This matrix establishes traceability between documented User Stories, corresponding Use Cases, and their associated UAT Test Cases. | [6 empty] | Passed
2. Each row reflects a tested scenario and confirms whether all expected behaviors were validated during UAT. | [6 empty] | Failed
Pending
Test Case ID | User Story ID | User Story Description | Use Case ID | Use Case Title | Report Page | Defect ID | Status
TC-01 | US-01 | Summary insights load | UC-01 | View Summary Page Insights | Summary | N/A | Passed
TC-02 | US-02 | Filter Overview KPIs by time | UC-03 | Filter Overview KPIs by Time | Overview | N/A | Passed
TC-03 | US-03 | Monitor churn by age group | UC-04 | Monitor Churn by Age group | Overview | N/A | Passed
TC-04 | US-04 | Deepa’s strategic view | UC-01 | View Summary Page Insights | Summary, Overview | N/A | Passed
TC-05 | US-05, US-06 | Revenue by region and product category | UC-05 | Review Revenue by Region & Category | Revenue | N/A | Passed
TC-06 | US-08, US-09 | View top products and ratings | UC-06 | View Top Products and Ratings | Products | N/A | Passed
TC-07 | US-10, US-11, US-12 | Campaign ROI and channel performance | UC-07 | Evaluate Campaign ROI & Conversions | Campaigns | N/A | Passed
TC-08 | US-15, US-16, US-17 | Track ticket volume and SLA resolution | UC-08 | Compare Ticket Trends & SLA | Support Tickets | N/A | Passed
TC-09 | US-19, US-20, US-21 | Analyze retention, churn by age/channel | UC-09 | Segment Customer Retention Insights | Customers | N/A | Passed
TC-10 | US-22, US-23 | QA filters and narrative definitions | UC-02, UC-10 | Validate Summary Metrics, QA Filters and Slicers Functionality | Summary, All Pages | N/A | Passed
TC-11 | US-25 | Test scheduled data refresh | UC-11 | Schedule Data Refresh Jobs | Back-end | N/A | Passed
TC-12 | US-27 | Role-based access | UC-12 | Apply Role-Level Security (RLS) | All Pages | N/A | Passed

## UAT Sign-Off
UAT Completion & Stakeholder Sign-Off
This document serves as official confirmation that the dashboard has successfully passed all UAT scenarios and is cleared for stakeholder review and presentation.
1. Project Summary Table |  | 2. Key Areas Covered |  | 3. Sign-Off Section
Field | Details | Item | Validated | Name | Role | Signature | Date
Project Name | Omnichannel Retail Behaviour and Performance Analytics Dashboard | Dashboard Page Access | Yes | Sudhagar | Business Intelligence Engineer | Signed | 2025-07-29
Version | 1 | KPI Logic and Definitions | Yes
Test Phase | UAT Final Functional & UI Testing | Filters and Slicers | Yes
Tested By | Sudhagar | Role-Based Access | Yes
Test Period | 2025-07-29 | Data Refresh Validation | Yes
Status | Completed | Visual Design/Layout Review | Yes
Total Test Cases | 12
Passed Test Cases | 12
Failed Test Cases | 0
High Priority Defects | 0
Dashboard Ready | Yes